## Calculator (Single Stage)
Traditional User Requirements |  |  |  | Queue Management Milestones
While Appendix J (ConsAg) dates have not traditionally been enforceable, it is useful to compare the new Milestones introduced under CMP376 against them in the first instance. |  |  |  | To support clients and the industry as a whole, Roadnight Taylor has developed a simple Milestone Calculator for transmission queue management. This free to use tool offers a view of milestone dates ahead of any Modification Application Offer or Construction Agreement Offer associated with a new application.
Please enter the details from the existing Construction Agreement (where applicable) to facilitate a comparison. |  |  |  | *Offer Date, Mod Application Offer Date or AtV Date.
| Project Name | Test Project |  | Project Name | Test Project
| Contract Number | XXXX1234_1 |  | Contract Number | XXXX1234_2
| Completion Date |  | (1st Completion Date in ConsAg) | Offer Date*
Completion Date
1 | The date by which the User expects to apply for Planning Consent based on its Connection Application |  |  | Number | Name | Deadline | Missed Deadline Impact
2 | The date by which the User expects Land Rights to be secured for the proposed development |  |  | Milestone 3 | Land Rights |  | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | 0
3 | The date by which the User expects to achieve Planning Consent |  |  | Milestone 1 | Initiate Planning Consent |  | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | 0
4 | Financial Investment Decision is achieved by the User |  |  | Milestone 2 | Secure Consent |  | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | 0
5 | The date by which the User's main procurement/construction and installation contracts have been let
6 | User to confirm to the Relevant Transmission Licensee the design of the User's substation bay |  |  | Milestone 4 | N/A
7 | The date by which final interface diagrams are exchanged and agreed between the Relevant Transmission Licensee and the User |  |  | Milestone 5 | Design Works Submission |  | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | 0
8 | Electromagnetic Transient Assessment data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 6 | Agree Construction Plan |  | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | 0
9 | Harmonic Performance Assessment data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 7 | Project Commitment |  | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | 0
10 | Protection and Control Facilities data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 8 | Initiate Construction |  | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | 0
11 | User First Site Access to the Relevant Transmission Licensee’s Connection Site
12 | User clear to start works at the Connection Site
13 | The date by which all User's Works are to be completed
14 | User clear to facilitate Commissioning Programme Commencement Date
Note the above is an example and can be edited to facilitate a full comparison as required.
Roadnight Taylor provide the information contained within this document for reference purposes only. Roadnight Taylor are not responsible for its accuracy or end use. no liability is accepted by Roadnight Taylor Limited for any loss, damage, expenses, charges or costs arising as a result of any decision, action or inaction of the applicable party or any other missed opportunities whatsoever arising from this Transmission Queue Management Tool, its content, use or interpretation.
Roadnight Taylor | Transmission Queue Management Tool

## Calculator (Multi Stage)
Traditional User Requirements |  |  |  | Queue Management Milestones
While Appendix J (ConsAg) dates have not traditionally been enforceable, it is useful to compare the new Milestones introduced under CMP376 against them in the first instance. |  |  |  | To support clients and the industry as a whole, Roadnight Taylor has developed a simple Milestone Calculator for transmission queue management. This free to use tool offers a view of milestone dates ahead of any Modification Application Offer or Construction Agreement Offer associated with a new application.
Please enter the details from the existing Construction Agreement (where applicable) to facilitate a comparison. |  |  |  | *Offer Date, Mod Application Offer Date or AtV Date.
| Project Name | Test Project |  | Project Name | Example Projec t
| Contract Number | XXXX1234_1 |  | Contract Number | XXXX1234_2
| Completion Date |  | (1st Completion Date in ConsAg) | Offer Date* | 2024-04-01
[6 empty] | Stage 1 | Stage 2 | Stage 3 | Stage 4
Completion Date
1 | The date by which the User expects to apply for Planning Consent based on its Connection Application |  |  | Number | Name | Stage 1 Deadline | Stage 2 Deadline | Stage 3 Deadline | Stage 4 Deadline | Missed Deadline Impact
2 | The date by which the User expects Land Rights to be secured for the proposed development |  |  | Milestone 3 | Land Rights | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
3 | The date by which the User expects to achieve Planning Consent |  |  | Milestone 1 | Initiate Planning Concent | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
4 | Financial Investment Decision is achieved by the User |  |  | Milestone 2 | Secure Consent | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Termination (unless evidence is provided within 60 days of the missed milestone specific exceptions apply) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
5 | The date by which the User's main procurement/construction and installation contracts have been let
6 | User to confirm to the Relevant Transmission Licensee the design of the User's substation bay |  |  | Milestone 4 | N/A
7 | The date by which final interface diagrams are exchanged and agreed between the Relevant Transmission Licensee and the User |  |  | Milestone 5 | Design Works Submission | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
8 | Electromagnetic Transient Assessment data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 6 | Agree Construction Plan | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
9 | Harmonic Performance Assessment data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 7 | Project Commitment | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
10 | Protection and Control Facilities data exchange as outlined in the Technical Appendices (Appendix F of the Bilateral Connection Agreement) |  |  | Milestone 8 | Initiate Construction | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Possible Termination (which is expected to be dependent on the applicability of exemptions and proposed timeline) | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated | Bilaterally Negotiated
11 | User First Site Access to the Relevant Transmission Licensee’s Connection Site
12 | User clear to start works at the Connection Site
13 | The date by which all User's Works are to be completed
14 | User clear to facilitate Commissioning Programme Commencement Date
Note the above is an example and can be edited to facilitate a full comparison as required.
Roadnight Taylor provide the information contained within this document for reference purposes only. Roadnight Taylor are not responsible for its accuracy or end use. no liability is accepted by Roadnight Taylor Limited for any loss, damage, expenses, charges or costs arising as a result of any decision, action or inaction of the applicable party or any other missed opportunities whatsoever arising from this Transmission Queue Management Tool, its content, use or interpretation.
Roadnight Taylor | Transmission Queue Management Tool

## Milestones
All durations referenced back from contracted Completion Date
Milestone |  | Name | Detail | Evidence | Milestone Dates
[5 empty] | 0 years to 2 years |  | 2 years to 3 years |  | 3 years to 4 years |  | 4 years to 5 years |  | 5 years and above
[5 empty] | 0 | 729 | 730 | 1094 | 1095 | 1459 | 1460 | 1824 | 1825 | Infinity
Conditional | M3 | Land Rights | The User must have secured the required land rights to enable the construction of the project. The Usermay be the owner/occupier of the land or has the necessary agreement from the owner/occupier. | The User shall provide documentation to demonstrate that:(i) The User is an owner or tenant of the land on which the proposed site is or will be situated; or (ii) The User has entered into an agreement to lease the land from the owner of the land on which the proposed site is or will be situated; or See table (varies with lead time)V1.03 V1.0 – 27 November 2023 (iii) The User has an option to purchase or to lease the land from the owner of the land on which the proposed site is or will be situated; or (iv) The User has entered into an exclusivity agreement in relation to the land with the owner of the land on which the proposed site is or will be situated; or (v) For an offshore site, the User has entered into an agreement for occupation or use of the seabed upon which the User's project (excluding any OTSDUW) is or will be located Nb the obligation is to secure and evidence the land right for the site of the installation e.g.Power Station or demand site so the evidence does not relate to rights e.g. easements associated with that site or OTSDUW. Compliance with this milestone is ongoing. | Bilaterally Negotiated |  | 21 |  | 27 |  | 39 |  | 51
| M1 | Initiate Planning Consent | Where statutory consents are required for the construction of the User’s project, the User must begin the process of seeking statutory consents, including Planning Permission for the project within the timescales and be able to provide the required evidence. | Submission of planning application to the relevant Statutory Authorityor, if the User’sproject does not require a statutory consent, a declaration from the User to that effect. | Bilaterally Negotiated |  | 18 |  | 24 |  | 36 |  | 48
| M2 | Secure Consent | Where required for the construction of the User’s project, the User must have secured statutory consents, including Planning Permission for the project within the timescales and be able to provide the required evidence. | The planning decision notice confirms planning permission has been granted and that this permission allows the User to meet the terms included in itsConstruction Agreement. Compliance with this milestone is ongoing. | Bilaterally Negotiated |  | 12 |  | 18 |  | 24 |  | 30
Construction | M4 | N/A - This milestone does not apply for Transmission
| M5 | Contestable Design Works Submission | This milestone will apply where a User has gone down the contestable route for connection. | Written confirmation from the Relevant Transmission Licensee that design obligations as bilaterally agreed in a User-Self Build agreement have been received. | Bilaterally Negotiated |  | 12 |  | 15 |  | 18 |  | 21
| M6 | Agree Construction Plan | The User must have agreed a construction plan for the detailed User’s Works with The Companywhich demonstrates how they will be progressing the User’s Works to achieve the Completion Date. | The User’s construction planshall demonstrate how the User will be ready for the Commissioning Programme Commencement Date and Completion Date. This must include a detailed programme for the User’s Works with a fixed start and end date as agreed with the Relevant Transmission Licensee, and be a programme aligned with the Commissioning Programme Commencement Date and Completion Date. | Bilaterally Negotiated |  | 9 |  | 12 |  | 15 |  | 18
| M7 | Project Commitment | This milestone demonstrates that the project has the necessary commitment or backing for it to proceed. | One of the following: • Binding contract issued by the User for main plant equipment; or • Capital contribution payments made to The Company in advance of connection; or • A decision paper from a formal, minuted meeting of the User’s board of directors evidencing Final Investment Decision (FID); or • award of agovernmental or regulatory subsidywhich provides financial support or incentive to the User’s project. | Bilaterally Negotiated |  | 6 |  | 9 |  | 12 |  | 15
| M8 | Initiate Construction | Project construction is the project phase i.e. the period from when a User begins the site works to carry out construction of its project until completion of the User’s Works | Commence construction according to theconstruction plan agreed under Milestone 6.Evidence for meeting this milestone will be a letter from the User’s board of directors or equivalent to state construction has commenced. | Bilaterally Negotiated |  | 3 |  | 6 |  | 9 |  | 12
Queue Management | Milestones

## Exceptions
A User Progression Milestone must be achieved by the date which represents the end of the milestone period identified for that milestone. The User Progression Milestones are categorised as Conditional Progression Milestones and Construction Progression Milestones. Different rights and obligations on National Grid ESO to terminate the User’s Construction Agreement apply for each of these categories. Once achieved a Conditional Progression Milestone must also continue to be met on an ongoing basis, that is, the statutory consent and planning permission initiated and secured and the land rights achieved to demonstrate compliance with the Conditional Progression Milestone must remain in place.
National Grid ESO will provide (in the form of Appendix Q) a Table based on the above with each Construction Agreement. This will specify the dates of the milestone periods for the User’s project derived in accordance with this Section 16 and set out in each Appendix Q.
Exceptional Issues on User Progression Milestones
There may be a small number of exceptional issues outwith the User’s control which may lead to User project delay and a User not being able to meet a User Progression Milestone.
The Exceptional issues which apply in the context of the Queue Management Process are as follows (see CUSC Section 16):
Where the User is delayed in carrying out the User’s Works which entitles the User to fix a later date or dates under Clause 3.2 of the Construction Agreement (Delays and Force Majeure) and that delay is the reason that a User Progression Milestone is not met;
Where the User is not able to meet a User Progression Milestone due to an event of Force Majeure;
Where delays caused by a party (other than the User, The Company or a Relevant Transmission Licensee) can be demonstrated to have an impact upon the User meeting a User Progression Milestone and the User could not have avoided these delays or their impact by the exercise of Good Industry Practice
Where a User is not able to meet a User Progression Milestone due to Planning appeals and third-party challenges in relation to the User’s Consents;
Any delay in the achievement of a milestone by the User which is caused by a Relevant Transmission Licensee or The Company.
Where the User believes an exceptional issue applies it shall provide written evidence to this effect supported by confirmation from the User’s board of directors or equivalent body for The Company’s consideration.
The summary of Queue Management exceptional issues and exepmtions has been taken from the V1.0 – 27 November 2023 "CUSC Section 16" legal text and Final Modification report. The latter suggests further guidance and excemption examples to follow from National Grid ESO, acknowledging that this would need to be kept "live" initially.
Roadnight Taylor provide the information contained within this document for reference purposes only . Roadnight Taylor are not responsible for its accuracy or end use.
Queue Management | Exceptions